# ICPS / NOMOS Partnership Plan 2026

# ICPS / NOMOS — Partnership Plan 2026

Electoral Community Marketing & Communications Campaign  |  April – December 2026

DRAFT

## Key Milestones

Late April 2026

Data collection begins; speaker recruitment opens

28 May 2026

Webinar — The Intelligence Edge

June – November 2026

Five awareness campaigns with follow-up

29 Nov – 3 Dec 2026

22nd International Electoral Awards — Manila

## Gantt Chart — Pre-Webinar Phase (April – May)

| Activity | W/C 27 Apr | W/C 4 May | W/C 11 May | W/C 18 May | W/C 25 May |
| --- | --- | --- | --- | --- | --- |
| Data |  |  |  |  |  |
| Database expansion (managerial tier) |  |  |  |  |  |
| Webinar Preparation |  |  |  |  |  |
| Speaker recruitment |  |  |  |  |  |
| Content & slides development |  |  |  |  |  |
| Run-sheet & logistics |  |  |  |  |  |
| Recruitment Emails |  |  |  |  |  |
| Email 1 — Save the date / announcement |  |  |  |  |  |
| Email 2 — Programme detail |  |  |  |  |  |
| Email 3 — Final reminder |  |  |  |  |  |
| ★ Webinar — 28 May |  |  |  |  | ★ |

## Gantt Chart — Campaign & Symposium Phase (June – December)

| Activity | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Data |  |  |  |  |  |  |  |
| Database expansion (ongoing) |  |  |  |  |  |  |  |
| Awareness Campaigns |  |  |  |  |  |  |  |
| Campaign 1 — Send & follow-up |  |  |  |  |  |  |  |
| Campaign 2 — Send & follow-up |  |  |  |  |  |  |  |
| Campaign 3 — Send & follow-up |  |  |  |  |  |  |  |
| Campaign 4 — Send & follow-up |  |  |  |  |  |  |  |
| Campaign 5 — Send & follow-up |  |  |  |  |  |  |  |
| Symposium & Awards |  |  |  |  |  |  |  |
| NOMOS presentation development |  |  |  |  |  |  |  |
| Exhibition & logistics |  |  |  |  |  |  |  |
| ★ Symposium & Awards — Manila |  |  |  |  |  | ★ | ★ |

## Deliverables by Component

| Component | ICPS Deliverables | Lead | Target Date |
| --- | --- | --- | --- |
| Data Collection | Expand database to include managerial-grade electoral contacts globally | ICPS | From late April |
| Recruitment Email 1 | Save-the-date / announcement email to full database | ICPS | ~30 April |
| Recruitment Email 2 | Programme detail and speaker spotlight | ICPS | ~4 May |
| Recruitment Email 3 | Final reminder with registration link | ICPS | ~18 May |
| Webinar | 1-hour event: speakers, facilitation, slides, run-sheet. Partner to advise on product messaging. | Joint | 28 May |
| Campaigns 1–5 | Editorial copy linking features to current electoral issues; follow-up calls by ICPS staff. Partner to review all copy. | Joint | Jun–Oct |
| Symposium Presentation | Fully aligned presentation in main conference programme | Joint | 29 Nov – 3 Dec |
| Exhibition Booth | Prime-position booth; ICPS coordinates logistics | ICPS | 29 Nov – 3 Dec |
| Award Presenting | Partner representative presents an award at the ceremony | ICPS | Awards night |
| Advocate Syndicate Room | Subject to webinar/campaign recruitment — room for advocates to present to symposium attendees | ICPS | TBC |

Core activity Ongoing / background Campaigns / emails ★ Major milestone

ICPS — Electoral Community Partnership 2026 Prepared by ICPS  |  electoralnetwork.org